## Risks
Risk ID | Category | Risk Description | Severity | Likelihood | Impact | Recommendation | Owner | Status
R-001 | Data Integrity | Hardcoded contact matching by name can update unintended person | High | Medium | Incorrect resource assignment visibility | Use a dedicated external ID/flag field for the seeded contact | Salesforce Admin | Open
R-002 | Configuration Drift | Global hierarchy names may differ across environments | Medium | Medium | Chain reset may skip target records | Store target keys in custom metadata and validate presence before update | Solution Architect | Open
R-003 | Security/FLS | Flow may fail for users lacking update permissions | Medium | Medium | Setup failure and partial execution | Restrict run access to setup permission set and add fault screen logging | Admin + Security | Open
R-004 | Operational | Flow intended for sign-up orgs might be run in non-target orgs | High | Low | Unexpected data changes in sandbox/prod | Add pre-check decision on org type/config before updates | Release Manager | Open
R-005 | Observability | No explicit fault path or retry guidance | Medium | Medium | Troubleshooting is harder for support teams | Add fault connectors + custom log object entry | Support Lead | Open

## Recommendations
Priority | Recommendation | Business Value | Technical Note
P1 | Replace hardcoded record name matching with custom metadata-driven keys | Improves reliability across org variants | Move filter constants to `CustomMetadata` and reference via Get Records
P1 | Introduce fault connectors and user-facing error screen | Reduces support ticket triage time | Capture `$Flow.FaultMessage` into a log object
P2 | Add one-time execution guard for org setup | Prevents accidental reruns | Persist setup completion flag in custom setting/metadata